## Slide 1: DEWG
Summary of preliminary work
Addis Ababa 2 May 2005

## Slide 2: Objectives for DOTS Expansion 2006-2015
To achieve, sustain and go beyond the "70/85" targets
2. To ensure equitable access to quality TB care for all people with TB, especially the poor (increasing access)
To reach MDGs

## Slide 3: Specific objectives of the planning exercise
To outline the expected DOTS expansion activities in the regions and in the world during 2006-2015
To estimate the resulting changes in case detection and treatment outcomes in regions during 2006-2015
To provide above data for
- modelling of impact on TB prevalence and death rate (MDGs)
- Estimate the regional and global cost of activities

## Slide 4: Past steps in developing DEWG plan
Jan/Feb 05: preparation of Montreux workshop,
- define strategic activities to increase CD and cure
- estimates of activities expansion (countries, regions)
- consultation with regions and some countries
- estimates on case detection and cure
- start costing
Feb 05: Montreux workshop
- revise estimates of activities expansion
- incorporate TB/HIV and DOTS plus interaction with DOTS expansion
- review estimates and costing
April 05:
- further consultation with regions and countries
- workshop in EMRO with key countries
- preparation of the draft plan
- core group of DEWG requests special teleconference to discuss the plan

## Slide 5: Next steps in developing DEWG plan
May 05:
- refine costing for countries and for support
- encourage regional workshops (good preparation for countries)
- teleconference with core group
- input from sub-groups
- complete plan
Jun 05:
- refine estimates and costings
- Global plan 2 to be presented to STAG and RA meetings
Jul – Oct:
- articulating DOTS Expansion – TB/HIV – DOTS plus activities
Oct 05:
- presentation of the plan to Mega meeting Versaille

## Slide 6: The DOTS Expansion scenario
The "Optimistic and realistic" scenario
  Efficient implementation of existing tools and strategies
  Expected impact on case detection and treatment outcome of combined DEWG activities (DOTS coverage, DOTS quality improvement and new approaches)

## Slide 7: From activities to impact and cost
Additional DOTS expansion activities in countries in relation to 2005 situation
Complete DOTS coverage (after 2005)
Improved DOTS quality (HR, laboratory, supervision, drug management)
Introduce/scale up PPM (int stand care)
Introduce/scale up Community DOTS
Introduce/scale up PAL
Increase capacity for Culture services and DST
Regional level outcomes:
CDR
Treatment success
Epidemiological impact
Country level cost units:
Number of cases to be treated
Additional population to be covered
7. Global and regional support for DOTS expansion, monitoring and evaluation and operational research
Cost
Number of cases x cost per treated case
Population covered x unit cost per population for activities under step 1-3
Global level cost units

## Slide 8: Overview of relevance of different types of DEWG related activities

## Slide 9: Estimating increased case detection and success rate
Estimate the expansion of activities that have an effect on case detection (increasing access) and cure (strengthening DOTS)
In consultation with regions and key countries
Estimates in high burden countries and countries with significant proportion of case load in region
Apply average relative increase in HBCs to non-HBCs in same region and calculate regional CDR

## Slide 10: DOTS expansion implementation: milestones to 2015

## Slide 11: Trends in additional population to be covered by different approaches

## Slide 12: Estimated regional treatment success rates 2002-2015

## Slide 13: Estimated regional new smear positive case detection trends 2003-2015

## Slide 14: Estimated cost for activities carried out by the DEWG

## Slide 15: 1. Countries that intensified DOTS implementation already in 2004-2005
Assuming that sustained intensification and/or more efficient use of available resources in those countries will be sufficient to improve quality implies that:
Cost per treated case in 2005 multiplied by number treated cases in a year = cost related to intensified DOTS that year
Thus, cost increase proportional to increase in case detection

## Slide 16: 2. Countries that need further intensification
Imagine a typical district with a given population size (500,000) in a typical country in the region (e.g. a rural district in Uganda)
Estimate required additional inputs in terms of HR, training, supervision, transport, supplies, etc
Estimate cost per 500,000 pop to be covered by intensified DOTS using country or regional cost data for above components
Multiply unit cost per population with population to be covered in country/region

## Slide 17: The Uganda / AFR example (DOTS intensification and community DOTS)
50,000 $US per district (500,000 pop)
0.1 $US per capita
500 million population in AFRhigh:
Additional 50 million per annum for DOTS quality improvement + community involvement

## Slide 18: Approach to costing new initiatives (step 3)
Define typical additional inputs needed:
Country level
Per additional population to be covered by the initiative
Differentiate between start up and running costs

## Slide 19: Ex: Costing additional PPM and community involvement
On "field level", PPM and Community DOTS costs the same or less than "conventional" DOTS
Start up and running costs only in relation to "support structures"
  Policy and guideline development
  National / provincial focal points and supervisors
  Task force / national partnerships
Unit costs on country level and by population to be covered

## Slide 20: Sustain 2005 costs for DOTS quality improvement, when coverage is 100%
20% CD increase

## Slide 21: Additional cost for DOTS quality improvement
Quality
20% CD increase
Quality

## Slide 22: Additional costs for DOTS quality improvement and new approaches
Quality
20% CD increase
Quality
New appr.
New appr.