## Slide 1: Working Group on New Drugs
“Operationalizing” the Strategic Plan
Stop TB Partnership Coordinating Board Meeting
Abuja, Nigeria
April 24-25, 2006

## Slide 2: Working Group Needs From the Strategic Plan
A robust and sustained new drug pipeline
Clinical trial capacity
Harmonized regulatory guidelines, fast-track approval
Animal models and validated surrogate markers
Biomarkers and surrogate endpoints
2006 – 2007 Focus
Notes: Sufficient clinical trial sites that meet GCP/GMP standards with trained personnel, sound infrastructure and appropriate procedures for patient recruitment, compliance and retention
Harmonized regulatory guidelines, including fast-track approval
A robust and sustained pipeline of new drug candidates and back-up programs
Animal models and validated surrogate markers broadly adopted by TB drug developers to aid in early identification of promising versus unpromising candidates
Biomarkers and surrogate endpoints to aid translational research and speed clinical development
Testing programs that enable more rapid and precise dose selection and optimization of complementary drug combinations

## Slide 3: Constraints
Incomplete landscape of TB compounds in development
Lack of detailed inventory of clinical trial sites
Dialogue with regulatory authorities on guidances nascent
Urgent need for funding - $3.6B gap for drugs alone (2006 - 2015)

## Slide 4
Need | WG Role/Activity | Timeline
Robust and sustained pipeline of new drug candidates and back-up programs | Conduct comprehensive mapping of the global TB drug portfolio via a web-based survey and make results available to WG members | • Survey launch: summer 2006 • Report finalization and presentation: fall 2006
Harmonized regulatory guidelines; fast-track approval | Organize and sponsor open forums on key regulatory issues in TB drug development with regulatory authorities, industry and WG members | • First conference: Washington, DC, December 2005 • Second conference: Europe, September 2006
Sufficient clinical trial sites meeting GCP/GMP standards | Collate and disseminate results of clinical trial site assessments by WG partners | Ongoing
Work Plan and Timeline