## Slide 1
Are we on track?
GLOBAL PLAN PROGRESS REPORT
2006-2008
Notes: <number>

## Slide 2
Joint project between Stop TB Partnership Working Groups, Secretariat, Partners and WHO TME Team
Summarizes the progress made (epi and finance) in implementing the Global Plan during its first three years: 2006-2008;
Describes actions taken by the international community of partners (contributions from the working groups)
Highlights the remaining challenges
Degree to which Global Plan targets have, or have not, been met.
Global Plan Progress Report
Notes: <number>
Data used, have been collected through the WHO annual survey. 2006 data, collected in 2007. 2007 and 2008 are preliminary data. Graphs will be updated with data collected this year.
Steering Committee has been established to guide the development of the progress report

## Slide 3: DOTS Global level
Notes: <number>
DOTS: continued to expand over the period 2006-2008. Targets for 2006 achieved globally for smear+.
Number of patients treated in DOTS prog exceeded the GP milestone (2.1 millions) for 2006.Same for 2007. Preliminary data for 2008 suggest the same trend: number of new smear-positive TB patients treated in DOTS programmes continued to increase worldwide, from 2.5 million (2006) to 2.6 million (2008) – far exceeding the Global Plan estimate. Targets almost achieved for smear-
Case detection rates for new smear+ cases continued to slowly increase (from 60% in 2005 to 61% in 2006). Far below the Global Plan target of 71% (calls into question the likelihood of achieving the 78% target set for 2010).
Number of new smear-negative and extrapulmonary cases treated in DOTS programmes – while increasing by more than 15% from 2006 to 2008 – is also lagging behind its Global Plan target.

## Slide 4: DOTS
Need to reinforce early and complete case detection
Notes: <number>
Case detection rate: at global level, not all the target were met. Far below the target for 2008 (71%).
Greatest increase over Global Plan estimates from 2006 to 2008: several regions did exceed Global Plan targets led by Eastern European countries (8% increase over its 2006 target). African countries, behind their targets (18% behind the 2006 target in African countries with a low HIV prevalence).

## Slide 5: DOTS
Increased political commitment and funding
HSS: Incorporation into Global Fund Proposals
TBTEAM – support for TA
Creation of the Global Lab Initiative
Development of "Guidance for national TB programmes on childhood TB care"
All TB high burden countries with PPM components
International Standards for TB Care (ISTC) disseminated;
DOTS: Further improve early and complete case detection
Lab: Creating conditions for accelerated laboratory strengthening, including private-sector involvement
HR: Crisis in many countries
TB& Poverty: In practice, free TB diagnosis and treatment not fully ensured
M&E: Collected data not optimally used for planning in countries
Major achievements
Remaining challenges
Notes: <number>
Although Global Plan targets for financing have not been met, there continues to be an overall increase in the monies available for TB control. These increased financial resources and efforts to implement the Stop TB Strategy have resulted in an increased demand for technical assistance.
More info on:
Childhood TB: - "Ethambutol efficacy and toxicity: literature review and recommendations for daily and intermittent dosage in children," & "A research agenda for childhood TB". - Policies developed by the subgroup partners incorporated in the "International Standards for TB Care" aimed at promoting high standards of TB care for all health care providers.
Lab strengthening: WHO policies established to ease and help improve the quality of services provided by country laboratory networks (revised definition of a new sputum smear-positive pulmonary TB case, endorsement of the use of liquid medium for culture and DST in middle- and low-income countries, followed by its use for rapid species identification to address the needs for culture and DST, endorsement of the use of line probe assays for rapid screening of patients at risk of MDR-TB
PPM: - Better perception among countries about the importance of engaging all care providers has changed - Focal person responsible for managing PPM-related activities in the central unit of the NTP Human resource dvt: Existing generic training modules for competence development for TB control at health facility and district level are being updated and new material, - Training courses and other learning opportunities on key aspects of comprehensive TB control organized at regional and inter-country level for key staff in NTPs and partners;
M&E: - Pilot test the MESST (Monitoring and Evaluation Strengthening System) tool, the DQA (Data Quality Audit) tool of the Global Fund to improve M&E planning and data quality within the Stop TB Strategy implementation

## Slide 6: MDR- TB
MDR-TB treatment vs. Global Plan targets, 2008
Need for scale up of high quality management of MDR-TB
Notes: <number>
GP targets for 2006. From 2007, inclusion of Response plan targets.
Changing in the landscape during the first three years of the Global Plan: emergence of XDR-TB,
As a result of additional funding for control of MDR-TB, there has been a rapid increase in the number of countries implementing MDR-TB. By July 2005, 36 MDR-TB Management projects treating more than 10,000 patients with MDRTB had been established in 27 countries.
Number of cases MDR-TB notified increased from 18,000 in 2005 to more than 46,000 (projected) in 2008 – an increase of more than 250%.
However, the number of MDR-TB patients to be treated was far behind the expectations of the Global Plan.
- Furthermore, scale up of high quality management of MDR-TB through the Green Light Mechanism continues to increase, the percentage of patients treated in such programmes in 2008 (21%) was far behind the Global Plan (56%).
- To build capacity for treating MDR-TB, quality-assured production of second-line drugs was established in two countries with a high MDR-TB burden (India and South Africa) by the end of 2008.

## Slide 7: MDR-TB
Increased number of countries using GLC
Universal access to MDR-TB diagnosis and treatment in some low resource countries (Peru)
Evidence that MDR-TB can be successfully managed even in high HIV prevalent countries
Updated Guidelines for the programmatic management of DR-TB
Evidence that up to 60% of XDR-TB can be cured in low HIV settings
Establishment of a research subgroup to develop an agenda
Very slow enrolment of patients
Drug procurement crisis and insufficient lab capacity
Unregulated quality and use of 1st and 2nd line drugs
Lack of political commitment
Lack of EQA laboratory networks
Quality of the routine data collected need to be improved
Lack of qualified human resources to implement MDR/XDR-TB programmes.
Major achievements
Remaining challenges
Notes: <number>

## Slide 8: TB/HIV
Notes: <number>
In 2006,
541,415 TB patients were tested for HIV compared with the Global Plan target of 1.6 million; 800,000 compared with 1.6 for 2008.
20% of TB patients were tested for HIV compared with the target of 47%

## Slide 9: TB/HIV
TB/HIV intervention scale-up, Africa *
Intervention, 2007 | Actual | Global Plan
% tested | 56% | 56%
% HIV+ TB on CPT | 75% | 90%
HIV+ TB on ART (000s) | 64 | 157
*Africa has 85% HIV+ TB cases globally
TB patients tested for HIV
HIV+ TB patients on CPT
HIV+ TB patients on ART
Notes: <number>

## Slide 10: TB/HIV
Scale-up HIV testing among TB patients
Increasing MDR/XDR in HIV prevalent settings, no tool to respond
Limitations of IPT at country level that must be addressed
Research efforts and funding must be intensified
Increasing MDR and XDR TB and non existent TB infection control
Weak monitoring and evaluation systems
Progress made in building commitment, communication and collaboration amongst key stakeholders
“Three Is”
Global Leaders' Forum on the co-epidemic, New York
Establishment of the TB Infection Control in October 2006
Major achievements
Remaining challenges
Notes: <number>
lagging far behind GP targets - due also to missing data from the HIV programmes.

## Slide 11: ACSM
Global Level
World TB Day 2007 and 2008
Encouraged and assisted business sector to engage in workplace and community action on TB
,
Engaged in advocacy initiatives - specific events
Calendar of priority advocacy events
Country level
Workshops on the effective use of communication tools to develop national ACSM strategies
Development of tools to facilitate advocacy
Building the capacity for ACSM at country level by establishing a platform for providing TA
Supported engagement of community representatives in ACSM planning
Finding innovative ways of engaging partners actively
Limited ACSM capacity in countries
Insufficient local data on knowledge, attitudes and practice for targeting ACSM activities and measure impact.
Major achievements
Remaining challenges
Notes: <number>

## Slide 12: Funding for TB control, 22 HBCs
All HBCs
HBCs excl. Russia and South Africa
Notes: <number>

## Slide 13
Funding vs. Global Plan, 22 HBCs
1.8
1.3
2.4
1.6
2.8
2.2
1.8
Gap of US$1 billion + 350m for MDR in countries other than RF and SA = US$1.4 billion
Technical assistance not shown
GP = Global Plan AF = Available Funding CP = Country Plan
Almost all the "green" for MDR-TB in country plans and available funding is S. Africa and Russia
Notes: <number>

## Slide 14
Developing new tools to diagnose TB
 | Target | Actual
Referral level |  | 
Introduction of new tools for rapid culture and DST | 2006 | Endorsed by WHO in 2007
Introduction of new tools for phage detection and DST | 2007 | Delayed
Introduction of new tools for automated NAAT | 2008 | Endorsed by WHO in 2008
Introduction of new tools for more rapid detection of smear-negative TB | 2008 | Endorsed by WHO in 2007
Peripheral laboratory |  | 
Introduction of new tools for improved microscopy | 2006 | More sensitive definition of a smear positive case: WHO, 2007
Introduction of simplified NAAT (Isothermal Amplification Assay) | 2008 | Delayed
Introduction of simplified NAAT (Quantitative PCR assay) | 2010 | n/a
Notes: <number>

## Slide 15: Diagnostics
Pipeline: 19 candidates at 3 levels (reference lab, peripheral level and health post)
Diagnostic pipeline: Roll-out of new or improved tools
Development of a scientific blueprint
Endorsement of new/improved diagnostics by WHO
Contribution to the development of a guide to the diagnostics pipeline for NTPs
Developing new tools to diagnose TB
Major achievements
Remaining challenges
More research is required into the use of existing diagnostics within clinical algorithms
More biomarker basic research for antigen discovery needed
Funding is needed for establishing/maintaining a platform of clinical trial sites for evaluation and demonstration studies.
Notes: <number>
Other contributions:
- Scientific blueprint: outlines steps and procedures for development and evaluation of new diagnostics and will serve as an objective basis for describing and staging diagnostic technologies in an up-to-date and inclusive pipeline of diagnostic technologies under development.
- Highlight the lack of basic knowledge for the development of new diagnostics for the early detection of TB (Grand challenges Exploration grant initiatives)
- Creation of a subgroup for Evidence Synthesis for TB Diagnostics
- Establishment of specific subgroups to focus specifically on optimized smear microscopy approaches, culture-based methods, nucleic acid amplification tests, point-of-care tests and tests for latent TB infection.
No info on budget

## Slide 16: Developing new drugs to treat TB
 |  |  | Target | Actual
Targets |  | Actual |  | 
By 2006 27 new compounds in the pipeline |  | 41 candidates in the pipeline 5 novel drug candidates in clinical trials - including the first 2 in development for MDR-TB; |  | 
By 2010 1-2 new drugs registered; treatment shortened to 3-4 months |  | n/a |  | 
By 2015 7 new drugs; treatment shortened to 1-2 months | n/a | n/a |  | 
Notes: <number>
Number of candidates in the pipeline in clinical trial are currently far too few to assure new TB drugs and regimens by dates in line with the Global Plan.
The 4 stages of dvt are translational basic research, discovery, preclinical and clinical
No information on budget

## Slide 17: Developing new drugs to treat TB
Pipeline: 41 candidates
5 novel drug candidates in clinical trials - including the first 2 in development for MDR-TB
Several trials addressing new indications for or optimization of existing drugs
Ongoing assessment and training of trial sites in GCP-compliance by trials consortia
Provided a forum for all stakeholders in TB drug development
Raised the profile of new TB drug R&D and promoted discussion with partners
Major achievements
Remaining challenges
Insufficient drug candidates: robust and sustained pipeline is needed (only 1 in 10 entering human trials reaches registration)
Clinical trial capacity: Insufficient GCP-compliant trials sites and lack of trial site networks
Lack of biomarkers to facilitate dose finding and shorten trials;
Lack of harmonized global regulatory guidelines
Notes: <number>
Number of candidates in the pipeline in clinical trial are currently far too few to assure new TB drugs and regimens by dates in line with the Global Plan.
The 4 stages of dvt are translational basic research, discovery, preclinical and clinical
No information on budget. Will be available next year.

## Slide 18: Developing new TB vaccines
 |  |  | Target | Actual
Targets |  | Actual |  | 
By 2006 5 vaccines in phase I trials |  | 8 vaccines candidates have entered clinical trials, and some have moved beyond Phase I. |  | 
By 2010 9 candidates in phase II trials; at least 2 vaccines in "proof of concept" trials; beginning phase III trials |  | Two vaccines candidates have entered Phase II clinical trials. |  | 
By 2015 4 phase III trials carried out. One safe, effective, licensed vaccine available |  | None |  | 
Notes: <number>

## Slide 19: Developing new TB vaccines
62 candidates in "Priming", Boosting" and "immunotherapy" categories
8 vaccine candidates in human clinical trials, 2 of which in phase II
Establishment of a task force to develop a standard definition of clinical endpoints
New collaborative research projects to focus on bacterial assays in a clinical setting
Major achievements
Remaining challenges
Identification of new vaccines candidates
Determining definitive diagnosis in infants and children
Clinical trials capacity: development of appropriate trial sites for large scale efficacy trials
Insufficient research funding for new tools
development and implementation
Notes: <number>
No information on budget requirements and progress. Will be available next year.

## Slide 20: Conclusions
DOTS
Continued to expand over the period 2006-2008. Targets for smear+ 2006 achieved. Case detection is stagnating.
MDR-TB
Number of patients to be treated is far behind the expectations of the GP/Response Plan targets
TB/HIV
Substantial increase of HIV testing for TB patients and TB testing for HIV patients globally,
Only few countries have reached or exceeded Global Plan targets
ACSM
Progress in bringing Stop TB advocacy partners to respond to TB issues; ACSM capacities at country level need to be reinforced; mobilization of resources required to achieve the GP targets did not have the results expected;
Research and development
Progress made in expanding the pipelines, diagnostics entering the field, progress in drugs and vaccines but not sufficient, greater funding for research and development is urgently needed
Notes: <number>
The first draft of the Progress report has been send to the steering committee for review and guidance