## Slide 1: WORKPLAN UPDATES
Coordinating Board Meeting
Tanzania, 28-29 October 2008

## Slide 2: WP Implementation as of 30 September 2008
PARTNERSHIP | Costs, US$ | Actual Implementation rate | Target rate
Approved planned cost | 15,294,600 | 32% | 38%
Budgeted cost | 6,764,310 | 72% | 75%
GLOBAL DRUG FACILITY | Costs, US$ | Actual Implementation rate | Target rate
Approved planned cost | 76,069,500 | 68% | 38%
Budgeted cost | 71,470,765 | 73% | 75%

## Slide 3: WP Implementation as of 30 September 2008
No | Partnership Area of Work (AoW) | Planned cost | Budget | Expenditure | Impl.rate vs Budget cost | Impl. rate vs. planned cost
1 | Country level ACSM | 1,225,000 | 933,516 | 283,324 | 30% | 23%
2 | Global advocacy | 2,006,000 | 1,038,249 | 756,659 | 73% | 38%
3 | Global Fund proposal preparation and implementation | 794,000 | 794,000 | 610,228 | 77% | 77%
4 | TB Profile enhancement | 1,290,000 | 302,783 | 258,124 | 85% | 20%
5 | Global communication | 1,000,000 | 425,872 | 347,865 | 82% | 35%
6 | Governance | 1,963,760 | 369,917 | 221,045 | 60% | 11%
7 | Partnership building | 2,125,840 | 779,976 | 421,937 | 54% | 20%
8 | Admin and financial mgt | 712,000 | 712,000 | 712,000 | 100% | 100%
9 | Support and innovation | 778,000 | 196,997 | 66,728 | 34% | 9%
10 | Total Support to Working Groups | 3,400,000 | 1,211,000 | 1,211,000 | 100% | 36%
 | GRAND TOTAL | 15,294,600 | 6,764,310 | 4,888,910 | 72% | 32%

## Slide 4: WP Implementation as of 30 September 2008
No. | GDF Area of Work | Planned cost | Budget cost | Expenditure | Impl. rate vs budget cost | Impl. rate vs planned cost
1 | Application review and monitoring | 1,983,000 | 1,249,265 | 766,293 | 61% | 39%
2 | Efficient supply of quality GDF products | 72,007,500 | 69,529,198 | 50,934,385 | 73% | 71%
3 | Procurement and supply activities | 1,062,000 | 268,313 | 146,705 | 55% | 14%
4 | GDF General Management | 1,017,000 | 423,989 | 254,941 | 60% | 25%
 | Total | 76,069,500 | 71,470,765 | 52,102,324 | 73% | 68%

## Slide 5: GOVERNANCE
Achievements
Independent External Evaluation satisfactorily completed
Responses to recommendations agreed, and accepted recommendations being implemented
Coordinating Board meeting successfully held (Egypt)
Three Executive Committee Teleconferences held
Challenges/Way Forward
Increased frequency of High Level Missions
Strategic use of the Board

## Slide 6: GLOBAL ADVOCACY
Achievements
Progress in the US – PEPFAR etc
HIV-TB Global Leaders Forum held in June 2008
EU & German – Parliamentary events, budget discussions ongoing
Establishment of the Centre for Resource Mobilization website
Challenges/Way Forward
Developing Strategic approach to advocacy in endemic "emerging economies" – India, China, Russia, Brazil, etc
Bi-lateral work with potential donors (Spain, Ireland etc)
Post election advocacy – US (from January) and EU (from July)
Resource Gap analysis - published
Curriculum on Resource Mobilization for partners
Research Movement

## Slide 7: Profiling TB: UN SG Special Envoy to Stop TB
– WTBD 08
Press conference with Chan, Piot, Kazatchkine
Launch of Figo's campaign in London
– HIV/TB Global Leaders Forum – UN, New York
Ban Ki-moon, Srgjan Kerim, Bill Clinton, Pres of Togo and Mozambique, First Ladies of Rwanda and Georgia, Chan, Piot, Kazatchkine, Dybul, Chesire, Zulu, and more than 60 ministerial delegations
Call for Action on HIV/TB
– Civil Society Forum on Health Issues for CPLP - Lisbon
– Clinton Global Initiative

## Slide 8: Profiling TB: Ambassadors
Luis Figo
– Poster/postcard campaign to Stop TB
Translated in 9 languages, launched in London APPG, distributed by Kempinski Hotels (53 locations) and Red Cross (189 countries), www.stoptb.org/figo , Burkina Faso: Ministry of Health through Total gas stations
– Comic Book on tuberculosis
Translated in 10 languages already and growing
– Media Coverage
BBC: Special feature on Figo, CNN: featured in report on HIV/TB
Anna Cataldi
– Missions to Afghanistan, Pakistan, Jordan
– Photo Book: "Tuberculosis: voices of the unheard"
– G8/2009

## Slide 9: ACSM (Country Level)
Achievements
Building capacity for ACSM at Country Level:
Workshops to help strategic implementation of Global Fund ACSM grants held in 4 WHO Regions. Specific country action plans developed
ACSM technical assistance coordinated in more than 10 countries
Essential ACSM tools for implementers developed: ACSM Handbook, KAP Survey Guide, Guiding Principles Community Involvement
Supporting quality health journalism:
Coordinated country-level journalist training planned in Paris during Union Conference 2008
Engagement with the HDnet to engage their network of country-level journalists in covering key TB-related issues

## Slide 10: ACSM (Country Level)
Challenges
ACSM capacity in countries and commitment to scale-up strategic activities remain low.
Best Practice document needed to get evidence of effectiveness of ACSM
Needs for countries to conduct KAP Survey or other operational research to better target ACSM activities and measure impact linked to TB control.

## Slide 11: Communication
Achievements
Support World TB Day – I am Stopping TB
Partners Forum site launched, including innovative e-discussion to build the Forum agenda
Strong media coverage of the HV/TB Global Leaders Forum, and placement of opinion pieces in ten targeted high-burden countries
Very broad media coverage of joint announcement between the Stop TB Partnership GDF, WHO, UNITAID and FIND about scaling up MDR-TB
Training workshops for journalists organized in Paris and Dar es Salaam
Challenges
One communication officer in the Secretariat

## Slide 12: PARTNERS ENGAGEMENT
Achievements
The Partnership welcomed 171 new partners, expanding its partner base from 589 to 760 partners as of October 2008
Eastern Mediterranean Stop TB Regional Partnership
National Stop TB Partnerships were established in Afghanistan, Japan and Vietnam.
Second Round of the Challenge Facility for Civil Society
Partners Forum preparations

## Slide 13: Global Drug Facility
Achievements
On track to reach 13M patient treatments delivered by end 2008
2 successful Technical Review and Business Advisory Committees meetings held
Target of increasing by 25% Global Fund Direct Procurement clients is on track
Establishment of effective stockpiles of first and second-line anti-TB drugs on track
GDF is on track to double the Number of Diagnostic Kit orders from '07 baseline & together with GLI/FIND secured $26.1M UNITAID approval for supply of new diagnostic tools from 2009
Objective of securing additional UNITAID funds for paediatric & second-line anti-TB drugs realized: US$ 56.4M approved

## Slide 14: CHALLENGES (cont.)
Increased all out effort will have to be made to procure drugs and carry out the required activities to use the money that has become available
  Working with WHO/EDM to increase the number of prequalified TB products particularly: 2nd line and pediatric drugs
  Overcoming barriers to effective access: importation restrictions, registration, market protection
  Marketing and strengthening of GDF's Direct Procurement Service; making it more self-sustaining
• A new business model based on close links with the business partners of GDF will have to be developed and implemented